## Sheet1
| Date | Responsible
Define information and timeline | 2024-10-16 | All
Run the analysis
1st review | 10/18/2024 5pm
Average Price Trends number of rooms | 10/18/2024 5pm | Ingrid
Bar | 10/18/2024 5pm | Gita
Pies ( sellers) | 10/18/2024 5pm | Gita
Linear regresion (Location) | 10/18/2024 5pm | Wisdom
Linear regresion (LandSize) | 10/18/2024 5pm | Wisdom
Linear regresion (#of rooms) | 10/18/2024 5pm | Mohammad
Linear regresion (Age) | 10/18/2024 5pm | Mohammad
Heat maps | 10/18/2024 5pm | Mohammad
show boxpot(price,location) | 10/18/2024 5pm | Ingrid
Price range # bathrooms whiskey | 10/18/2024 5pm | Ingrid
chi-square | 10/18/2024 5pm | Wisdom
Analysis 3 #rooms whiskey | 10/18/2024 5pm | Ingrid
Mohamed consolidation in the system
Prepare presentation | 2024-10-22
Challenges
Post analysis to be done
Presentation to Krystyna | 2024-10-23

## Sheet2
Hypothesis
melhousingclean_df['Date'] = pd.to_datetime(df['Date'], format='%Y-%m-%d')
melhousingclean_df['Date'] = melhousingclean_df['Date'].dt.strftime('%m/%d/%Y')
column= {"Date":[]}
melhousingclean_df=pd.DataFrame(column)
melhousingclean_df["Date"] = pd.to_datetime(melhousingclean_df["Date"])
melhousingclean_df["Date"] = melhousingclean_df["Date"].dt.strftime("%Y-%m-%d")
print(melhousingclean_df)